## Formula calculated due dates
EVENT TITLE
EVENT DATE | 2020-11-01
PRODUCTION TIMELINE - ONLINE EVENT
WHO | DELIVERABLE | SUGGESTED LEAD TIME | DUE DATE | COMPLETED
| Pre-event planning meeting with stakeholders | 12-8 weeks prior | 2020-08-09
| Submit PIF for Marketing support | 12-8 weeks prior | 2020-08-09
| Determine speakers | 12-8 weeks prior | 2020-08-09
| Create budget | 7 weeks prior | 2020-09-13
| Determine audience, work with Marketing for support | 7 weeks prior | 2020-09-13
| Draft email invite content to be shared with Marketing | 6 weeks prior | 2020-09-20
| Draft RSVP content to be shared with Marketing | 6 weeks prior | 2020-09-20
| Coordinate invite information with Marketing team | 6-3 weeks prior | 2020-09-20
| Send invite with final RSVP link (tier 1) -- update date per Marketing | 5 or 4 weeks prior | 2020-09-27
| Send invite with final RSVP link (tier 2, if needed) -- update date per Marketing | 4 or 3 weeks prior | 2020-10-04
| Begin briefing to be delivered to stakeholders week of event | 2 weeks prior | 2020-10-18
| Create Zoom link | 2 weeks prior | 2020-10-18
| Finalize attendee list; send reminder email for top-priority guests to sign-up, or individual reminders to tier 1 guests who have not responded | 1 week prior | 2020-10-25
| Send reminder email to all attendees with Zoom link | 1 week prior | 2020-10-25
| Prep / pre-event meeting with speaker(s) to verify technical needs are good | 1 week prior | 2020-10-25
| Event |  | 2020-11-01
| Send post-event thank you email | 1-2 days post | 2020-11-02
| Submit final attendance list for an Activity Code assignment | 1 day post | 2020-11-02
| Review and finalize budget, if needed | 1 week post | 2020-11-08
Note on B4: Kate Mortensen: update this date cell to change all dates below
Note on B10: Kate Mortensen: PIF must be submitted 8 weeks in advance of sending INVITES PIF Needed if… --This is a cross-department event, public event, or large event, --This is an event that utilizes a platform other than Zoom, --You need a special list curated or pulled, --You need a branded Marketo email or Cvent RSVP page, --You need other specialty branded materials not listed on the Toolkit

## Weeks Days Formula
Weeks to days for formula |  |  | When should your event be?
Language | Weeks | Days | Today | 2021-12-17 | Enter a planning start date: | 2021-01-25
12 weeks prior | 12 | 84 | 8-week lead time | 2021-10-22 | 8-week lead time | 2020-12-04
11 weeks prior | 11 | 77
10 weeks prior | 10 | 70
9 weeks prior | 9 | 63
8 weeks prior | 8 | 56
7 weeks prior | 7 | 49
6 weeks prior | 6 | 42
5 weeks prior | 5 | 35
4 weeks prior | 4 | 28
3 weeks prior | 3 | 21
2 weeks prior | 2 | 14
1 weeks prior | 1 | 7
6 days prior |  | 6
5 days prior |  | 5
4 days prior |  | 4
3 days prior |  | 3
2 days prior |  | 2
1 days prior |  | 1
0 days prior |  | 0
1 day post |  | 1
2 days post |  | 2
3 days post |  | 3
1 week post | 1 | 7
1 month post | 4.5 | 31.5
Note on C2: Kate Mortensen: Use the # of days in the formula on the other sheet.