# GENERAL EVENT PRODUCTION TIMELINE

| Within Four Months Before the Event Date |  |
| --- | --- |
|  | Identify strategic goals. |
|  | Identify target audience and key stakeholders. |
|  | Begin determining event program and speakers. |
|  | Identify event budget and appropriate Workday Work Tags. |
|  | Research and gather quotes for possible vendors and venues. |
|  | Create an event communications timeline that outlines invitation send dates. |
|  | Determine which event registration platform is necessary. (i.e. Cvent, Trumba, Microsoft Forms) |
|  | Submit Project Inquiry Forms (PIFs) for event and marketing support, as needed. |
|  | Draft an event description. |
| Within Three Months Before the Event Date |  |
|  | Confirm the date, time, and location. |
|  | Complete a University Use of Facilities Form (UUF). |
|  | Begin evaluating your catering plan and determine if a UW Temporary Food Establishment Permit is necessary. |
|  | Select a caterer and other key vendors. |
|  | Finalize the event description and marketing/communications timeline. |
| Within Two Months Before the Event Date |  |
|  | Contract vendors and pay deposits. |
|  | Complete Alcohol Service Request Form (ASR). |
| 6 Weeks Before the Event Date |  |
|  | Confirm special guest list, as necessary. |
|  | Determine need for event staff. |
|  | Complete Alcohol Service Request Form (ASR). |
|  | Submit a UW Temporary Food Establishment Permit form. |
| 4 Weeks Before the Event Date |  |
|  | Recruit volunteers to staff the event. |
|  | Draft program timeline and share with guest speakers. |
| 2 weeks Before the Event Date |  |
|  | Design and print event signage and check-in materials. |
|  | Finalize logistics timeline and provide to event staff. |
|  | Submit a request for OnArrival iPads and other equipment with the CAS Event Equipment Rental Request Form. |
| 1 week before |  |
|  | Inform event staff and volunteers of their duties, logistics timeline, what to wear, etc. |
|  | Email to registrants with updates, information and reminders |
|  | Gather needed equipment and supplies |
| 3 business days before the event |  |
|  | Submit final catering number and allergen reports to catering team. |
| Day of Event |  |
|  | Complete event set up. |
|  | Take photos of the event. |
|  | Share your cell phone number with vendors and volunteers for quick responses |
|  | Complete event tear down. |
| Post Event (1 Week past) |  |
|  | Send written thank you notes to guest speakers and key volunteers. |
|  | Review all expenses and ensure contracts are properly invoiced. |
|  | Complete a post-event debrief meeting. |
|  | Finalize all post event reporting documents, as necessary. |
|  | Record event activity into Tandem OR ensure Cvent registration data has synced into Tandem |